## For Airmaniax Client
Project | Team | Event | Status | Description (if any) | Timeline or date | Comments /links
AirManiax | Ads | Received all access | Completed |  | 2025-06-27
StreetManiax | Ads | Received all access | Completed |  | 2025-06-27
AirManiax | Tech | Recevied access to all tools | Completed | Except FTP - since it was not required earlier Google Search Console | 2025-06-27
StreetManiax | Tech | Recevied access to all tools | Completed | Except FTP - since it was not required earlier Google Search Console Google Analytics | 2025-06-27
AirManiax | Tech | Website backend understanding | Completed | From our end - on the documents shared | 2025-06-30
StreetManiax | Tech | Website backend understanding | Completed | From our end - on the documents shared | 2025-06-30
AirManiax | SEO/GEO/Emailer | Keyword research | Completed |  | 2025-07-01
StreetManiax | SEO/GEO/Emailer | Keyword research | Completed |  | 2025-07-01
AirManiax | SEO/GEO/Emailer | 3 months plan - Blogs, faqs (SEO and GEO) | Completed |  | 2025-07-01
StreetManiax | SEO/GEO/Emailer | 3 months plan - Blogs, faqs (SEO and GEO) | Completed |  | 2025-07-01
AirManiax | Ads | Next steps on structural fixes | Completed | Other than phone numbers | 2025-07-07
StreetManiax | SEO/GEO/Emailer | Set up Google Search Console | Completed | It did no exist on account, set it up from our end | 2025-07-07
AirManiax | SEO/GEO/Emailer | Set up Google Search Console | Completed | It did no exist on account, set it up from our end | 2025-07-07
AirManiax | Tech | Set up Google Search Console | Completed | It did no exist on account, set it up from our end | 2025-07-07
StreetManiax | Tech | Set up Google Search Console | Completed | It did no exist on account, set it up from our end | 2025-07-07
AirManiax | Ads | Clarification on doubts | Completed | Phone numbers - No Changes | 2025-07-11
AirManiax | Ads | Demographic changes | Completed | 25-54 + Top 30% Income + Parent | 2025-07-11
AirManiax | Ads | Keywords review & expansion | Completed | Search terms are relevant | 2025-07-12
AirManiax | Ads | Keyword match type changes & optimisation | Completed | Broad Match until feedback on lead volume by 1 week | 2025-07-12
AirManiax | Ads | Bidding strategy review | Completed | Conv Max | 2025-07-13
AirManiax | SEO/GEO/Emailer | Updated 1 blog on the live website | Completed | The alignment is a bit off and we are unbale to make changes on the live website, awaiting FTP access | 2025-07-15
StreetManiax | SEO/GEO/Emailer | Updated 1 blog on the live website | Completed | The alignment is a bit off and we are unbale to make changes on the live website, awaiting FTP access | 2025-07-15
AirManiax | SEO/GEO/Emailer | 1 emailer for a campaign | Completed | Completed and tested internally, but needs to be discussed with Client | 2025-07-15
StreetManiax | SEO/GEO/Emailer | 1 emailer for a campaign | Completed | Completed and tested internally, but needs to be discussed with the Client | 2025-07-15
AirManiax | Tech | Website backend understanding | Completed | On a call with Prakhar | 2025-07-15
StreetManiax | Tech | Website backend understanding | Completed | On a call with Prakhar | 2025-07-15
AirManiax | SEO/GEO/Emailer | 1 blog written in English | Completed |  | 2025-07-15
StreetManiax | SEO/GEO/Emailer | 5 blogs written in English | Completed |  | 2025-07-15
AirManiax | Ads | Ad copies revision | Completed | To increase the CTR | 2025-07-16
StreetManiax | Tech | Setting up Google Analytics | Completed | Will be setting it up for better tracking | 2025-07-16
AirManiax | Ads | Post Changes Monitoring | Completed | Next Optimisation on 17-Jul-2025 | 2025-07-17
AirManiax | SEO/GEO/Emailer | Changing the information architecture to fit the SEO and GEO plan | Completed | requested on 15th and received FTP access on 16th. In progress | 2025-07-17
StreetManiax | SEO/GEO/Emailer | Changing the information architecture to fit the SEO and GEO plan | Completed | requested on 15th and received FTP access on 16th. In progress | 2025-07-17
AirManiax | Tech | Changing the information architecture to fit the SEO and GEO plan | Completed | All done from our end. Sent the document of requirement to Prakhar over the whatsapp group, waiting for response. | 2025-07-17
StreetManiax | Tech | Changing the information architecture to fit the SEO and GEO plan | Completed | All done from our end. Sent the document of requirement to Prakhar over the whatsapp group, waiting for response. | 2025-07-17
StreetManiax | Ads | Campaign Paused | Completed | URL not working | 2025-07-21
AirManiax | Ads | Revising attribution model | Completed | 30 days click to 3 week | 2025-07-21
AirManiax | Ads | Negative keyords revise | Completed | Search campaigns | 2025-07-21
AirManiax | Ads | Call number asset added to the asset | Completed | Search campaigns | 2025-07-21
AirManiax | Ads | Structure snippets asset added | Completed | Search campaigns | 2025-07-21
AirManiax | Ads | 10% budget increased in the Pmax campaign | Completed | To improve conversions and ads score. | 2025-07-23
AirManiax | SEO/GEO/Emailer | Blog Section issues | Completed | Font issues and alignment fixed | 2025-07-23
AirManiax | SEO/GEO/Emailer | Changing the information architecture to fit the SEO and GEO plane | Completed | Request sent to Prakhars team | 2025-07-24
StreetManiax | SEO/GEO/Emailer | Changing the information architecture to fit the SEO and GEO plane | Completed | Request sent to Prakhars team | 2025-07-24
AirManiax | Ads | Bid strategy changed | Completed | Bid strategy changed from conversion value to maximise conversions | 2025-07-25
AirManiax | Ads | More negative keywords added to campaigns | Completed | Keywords related to mall contact no etc | 2025-07-25
AirManiax | SEO/GEO/Emailer | All English and Arabic blogs written and sent over email on 25th July | Completed |  | 2025-07-25
StreetManiax | SEO/GEO/Emailer | All English and Arabic blogs written and sent over email on 25th July | Completed |  | 2025-07-25
AirManiax | SEO/GEO/Emailer | Awaiting Input from the client on arabic content on emailer 1 | Awaiting input |  | 2025-07-29
StreetManiax | SEO/GEO/Emailer | Awaiting Input from the client on arabic content on emailer 1 | Awaiting input |  | 2025-07-29
AirManiax | Ads | Ad assets | Completed |  | 2025-07-29
StreetManiax | Ads | Ad assets | Completed |  | 2025-07-29
AirManiax | Ads | Asset inventory refresh through new YouTube videos for PMax campaign. | Completed | Will upload New/Instagram videos on YouTube to use in ads. | 2025-07-31
AirManiax | Ads | New image/video assets for Pmax campaigns. | Completed | marked some new themes to build new content to reduce ads fatigue and more engagement. | 2025-07-31
AirManiax | SEO/GEO/Emailer | Meta titles and tags updated | Completed |  | 2025-07-31
StreetManiax | SEO/GEO/Emailer | Meta titles and tags updated | Completed |  | 2025-07-31
StreetManiax | SEO/GEO/Emailer | Set up Google Ads for SM | Completed |  | 2025-07-31
AirManiax | Ads | First party data (email) upload on the Google ads account | In-Progress | Team will provide the data | 2025-07-31
StreetManiax | Ads | New Google ad account created | Completed |  | 2025-08-02
AirManiax | SEO/GEO/Emailer | Emailer 2 written and sent | Completed |  | 2025-08-04
StreetManiax | SEO/GEO/Emailer | Emailer 2 written and sent | Completed |  | 2025-08-04
StreetManiax | Tech | Updated a plugin on SM (email sent by Riyaz by Hostinger) | Completed |  | 2025-08-04
AirManiax | SEO/GEO/Emailer | Feedback from stephen on emailer | Completed |  | 2025-08-05
StreetManiax | SEO/GEO/Emailer | Feedback from stephen on emailer | Completed |  | 2025-08-05
AirManiax | Tech | Awaiting confirmation from Prakhar on the dev of changes given | Completed |  | 2025-08-05
StreetManiax | Tech | Awaiting confirmation from Prakhar on the dev of changes given | Completed |  | 2025-08-05
StreetManiax | Ads | New Google tags created and shared for implementation | Completed | to track ads' performance | 2025-08-05
AirManiax | Ads | New image/video assets for Pmax campaigns. | Completed | marked some new themes to build new content to reduce ads fatigue and more engagement. | 2025-08-06
AirManiax | Ads | First party data (email) upload on the Google ads account | In-Progress | Team will provide the data | 2025-08-06
StreetManiax | Ads | Setting up Google Ads: https://ads.google.com/aw/billing/billingsetups?ocid=7474855848&ascid=7474855848&euid=1404235817&__u=4274393633&uscid=7469980266&__c=4486375834&authuser=2&__e=1556230347 | Awaiting input | Need payment details on the account. | 2025-08-06
AirManiax | Ads | Google tag implementation on roller.app payment page | In-Progress | To track conversion and refined remarketing/signals campaigns | 2025-08-06
AirManiax | Ads | Update the text ads with new copies | Completed | To refresh ads with improvised text copies | 2025-08-08
AirManiax | Ads | Awareness campaign on YouTube | On-hold | To increase the reach to customers | 2025-08-09
AirManiax | Ads | DSA ads created in the search campaign | Completed | 2 new ads created with new copies for ad quality improvement testing | 2025-08-10
AirManiax | Ads | DSA ads created in the search campaign | Completed | 2 new ads created with new copies for ad quality improvement testing | 2025-08-10
AirManiax | Ads | Campaign quality score for better optimisation | Completed | 90% score for Pmax and search campaign. | 2025-08-11
AirManiax | Ads | Campaign quality score for better optimisation | Completed | 90% score for Pmax and search campaign. | 2025-08-11
AirManiax | SEO/GEO/Emailer | Posted all English Blogs | Completed |  | 2025-08-12
StreetManiax | SEO/GEO/Emailer | Posted all English Blogs | Completed |  | 2025-08-13
AirManiax | Ads | Pmax Al Ain outlet Launch Campaign with offers from 15 Aug to 17 Aug | Completed | Launch Offers | 2025-08-15
AirManiax | Ads | Search Al Ain outlet Launch Campaign with offers from 15 Aug to 17 Aug | Completed | Launch Offers | 2025-08-15
AirManiax | Ads | Video View and Awareness Al Ain outlet Launch Campaign with offers from 15 Aug to 17 Aug | Completed | Launch Offers | 2025-08-15
AirManiax | SEO/GEO/Emailer | Al Ain launch emailer sent to the whole database | Completed |  | 2025-08-15
AirManiax | Ads | Pmax Al Ain outlet Launch Campaign with offers from 15 Aug to 17 Aug | Completed | Launch Offers | 2025-08-15
AirManiax | Ads | Search Al Ain outlet Launch Campaign with offers from 15 Aug to 17 Aug | Completed | Launch Offers | 2025-08-15
AirManiax | Ads | Video View and Awareness Al Ain outlet Launch Campaign with offers from 15 Aug to 17 Aug | Completed | Launch Offers | 2025-08-15
AirManiax | Ads | Actual sales mapping with campaigns performance. | On-hold | To assess the impact of campaigns with a change in the optimization strategy. Client does not have data of this to share with us. | 2025-08-17
AirManiax | Ads | Actual sales mapping with campaigns performance. | On-hold | To assess the impact of campaigns with a change in the optimization strategy. Client does not have data of this to share with us. | 2025-08-17
AirManiax | SEO/GEO/Emailer | Waiting for input on July 2nd emailer | Awaiting input |  | 2025-08-19
StreetManiax | SEO/GEO/Emailer | Waiting for input on July 2nd emailer | Awaiting input |  | 2025-08-19
AirManiax | SEO/GEO/Emailer | Awating input on all Arabic blogs after making the English version as requested | Awaiting input |  | 2025-08-20
StreetManiax | SEO/GEO/Emailer | Awating input on all Arabic blogs after making the English version as requested | Awaiting input |  | 2025-08-20
AirManiax | Ads | Daily Budget Revision | Completed | Budget increased from AED180 to AED225
AirManiax | Ads | WhatsApp extension added | On-hold | Waiting for the client to let us know about Wati

## Content - SEOGEOEmailer
Project | Team | Event | Status | Description (if any) | Timeline or date | Comments /links
AirManiax | SEO/GEO/Emailer | Keyword research | Completed |  | 2025-07-01
StreetManiax | SEO/GEO/Emailer | Keyword research | Completed |  | 2025-07-01
AirManiax | SEO/GEO/Emailer | 3 months plan - Blogs, faqs (SEO and GEO) | Completed |  | 2025-07-01
StreetManiax | SEO/GEO/Emailer | 3 months plan - Blogs, faqs (SEO and GEO) | Completed |  | 2025-07-01
StreetManiax | SEO/GEO/Emailer | Set up Google Search Console | Completed | It did no exist on account, set it up from our end | 2025-07-07
AirManiax | SEO/GEO/Emailer | Set up Google Search Console | Completed | It did no exist on account, set it up from our end | 2025-07-07
AirManiax | SEO/GEO/Emailer | Updated 1 blog on the live website | Completed | The alignment is a bit off and we are unbale to make changes on the live website, awaiting FTP access | 2025-07-15
StreetManiax | SEO/GEO/Emailer | Updated 1 blog on the live website | Completed | The alignment is a bit off and we are unbale to make changes on the live website, awaiting FTP access | 2025-07-15
AirManiax | SEO/GEO/Emailer | Changing the information architecture to fit the SEO and GEO plane | Completed | requested on 15th and received FTP access on 16th. In progress | 2025-07-17
StreetManiax | SEO/GEO/Emailer | Changing the information architecture to fit the SEO and GEO plane | Completed | requested on 15th and received FTP access on 16th. In progress | 2025-07-17
AirManiax | SEO/GEO/Emailer | 1 emailer for a campaign | Completed | Completed and tested internally, but needs to be discussed with the team | 2025-07-15
StreetManiax | SEO/GEO/Emailer | 1 emailer for a campaign | Completed | Completed and tested internally, but needs to be discussed with the team | 2025-07-15
AirManiax | SEO/GEO/Emailer | 1 blog written in English | Completed |  | 2025-07-15
StreetManiax | SEO/GEO/Emailer | 5 blogs written in English | Completed |  | 2025-07-15
AirManiax | SEO/GEO/Emailer | Blog Section issues | Completed | Font issues and alignment fixed in Al Quoz Dubai. Sample blog is also published. | 2025-07-23
AirManiax | SEO/GEO/Emailer | Changing the information architecture to fit the SEO and GEO plane | Completed | Request sent to Prakhars team | 2025-07-24
StreetManiax | SEO/GEO/Emailer | Changing the information architecture to fit the SEO and GEO plane | Completed | Request sent to Prakhars team | 2025-07-24
AirManiax | SEO/GEO/Emailer | All English and Arabic blogs written and sent over email on 25th July | Completed |  | 2025-07-25
StreetManiax | SEO/GEO/Emailer | All English and Arabic blogs written and sent over email on 25th July | Completed |  | 2025-07-25
AirManiax | SEO/GEO/Emailer | Emailer 2 written and sent | Completed |  | 2025-08-04
StreetManiax | SEO/GEO/Emailer | Emailer 2 written and sent | Completed |  | 2025-08-04
AirManiax | SEO/GEO/Emailer | Meta titles and tags updated | Completed |  | 2025-07-31
StreetManiax | SEO/GEO/Emailer | Meta titles and tags updated | Completed |  | 2025-07-31
AirManiax | SEO/GEO/Emailer | Awaiting Input from the client on arabic content on emailer 1 | Completed |  | 2025-07-29
StreetManiax | SEO/GEO/Emailer | Awaiting Input from the client on arabic content on emailer 1 | Completed |  | 2025-07-29
AirManiax | SEO/GEO/Emailer | Feedback from stephen on emailer | Completed |  | 2025-08-05
StreetManiax | SEO/GEO/Emailer | Feedback from stephen on emailer | Completed |  | 2025-08-05
StreetManiax | SEO/GEO/Emailer | Set up Google Ads for SM | Awaiting input | Accounts team is unable to add details here. | 2025-07-31
AirManiax | SEO/GEO/Emailer | Posted all English Blogs | Completed |  | 2025-08-12
StreetManiax | SEO/GEO/Emailer | Posted all English Blogs | Completed |  | 2025-08-13
AirManiax | SEO/GEO/Emailer | Al Ain launch emailer sent to the whole database | Completed |  | 2025-08-15
AirManiax | SEO/GEO/Emailer | Waiting for input on July 2nd emailer | Awaiting input |  | 2025-08-19
StreetManiax | SEO/GEO/Emailer | Waiting for input on July 2nd emailer | Awaiting input |  | 2025-08-19
AirManiax | SEO/GEO/Emailer | Awating input on all Arabic blogs after making the English version as requested | Awaiting input |  | 2025-08-20
StreetManiax | SEO/GEO/Emailer | Awating input on all Arabic blogs after making the English version as requested | Awaiting input |  | 2025-08-20

## Website
Project | Team | Event | Status | Description (if any) | Timeline or date | Comments /links
AirManiax | Tech | Website backend understanding | Completed | From our end - on the documents shared | 2025-06-30
StreetManiax | Tech | Website backend understanding | Completed | From our end - on the documents shared | 2025-06-30
AirManiax | Tech | Website backend understanding | Completed | On a call with Prakhar | 2025-07-15
StreetManiax | Tech | Website backend understanding | Completed | On a call with Prakhar | 2025-07-15
AirManiax | Tech | Recevied access to all tools | Completed | Except FTP - since it was not required earlier Google Search Console | 2025-06-27
StreetManiax | Tech | Recevied access to all tools | Completed | Except FTP - since it was not required earlier Google Search Console Google Analytics | 2025-06-27
AirManiax | Tech | Set up Google Search Console | Completed | It did no exist on account, set it up from our end | 2025-07-07
StreetManiax | Tech | Set up Google Search Console | Completed | It did no exist on account, set it up from our end | 2025-07-07
AirManiax | Tech | Changing the information architecture to fit the SEO and GEO plan | Completed | All done from our end. Sent the document of requirement to Prakhar over the whatsapp group, waiting for response. | 2025-07-17
StreetManiax | Tech | Changing the information architecture to fit the SEO and GEO plan | Completed | All done from our end. Sent the document of requirement to Prakhar over the whatsapp group, waiting for response. | 2025-07-17
StreetManiax | Tech | Setting up Google Analytics | Completed | Will be setting it up for better tracking | 2025-07-16
StreetManiax | Tech | Setting up Google Ads | On-hold | Stephen asked us to pause on ads for SM
AirManiax | Tech | Awaiting confirmation from Prakhar on the dev of changes given | Completed |  | 2025-08-05
StreetManiax | Tech | Awaiting confirmation from Prakhar on the dev of changes given | Completed |  | 2025-08-05
StreetManiax | Tech | Updated a plugin on SM (email sent by Riyaz by Hostinger) | Completed |  | 2025-08-04

## Ads
Project | Team | Event | Status | Description (if any) | Timeline or date | Comments /links
AirManiax | Ads | Received all access | Completed |  | 2025-06-27
StreetManiax | Ads | Received all access | Completed |  | 2025-06-27
AirManiax | Ads | Ad assets | Completed
StreetManiax | Ads | Ad assets | On-hold
AirManiax | Ads | Clarification on doubts | Completed | Phone numbers - No Changes | 2025-07-11
StreetManiax | Ads | Clarification on doubts | On-hold | On hold as per the client
AirManiax | Ads | Next steps on structural fixes | Completed | Other than phone numbers | 2025-07-07
AirManiax | Ads | Demographic changes | Completed | 25-54 + Top 30% Income + Parent | 2025-07-11
AirManiax | Ads | Keywords review & expansion | Completed | Search terms are relevant | 2025-07-12
AirManiax | Ads | Keyword match type changes & optimisation | Completed | Broad Match until feedback on lead volume by 1 week | 2025-07-12
AirManiax | Ads | Bidding strategy review | Completed | Conv Max | 2025-07-13
AirManiax | Ads | Ad copies revision | Completed | To increase the CTR | 2025-07-21
AirManiax | Ads | Post Changes Monitoring | Completed | Next Optimisation on 17-Jul-2025 | 2025-07-17
StreetManiax | Ads | Campaign Paused | Completed | URL not working | 2025-07-21 | https://streetmaniax.com/lp/indoor-adventure-park-in-dubai-2/%7Bignore?utm_source=googleads&vt_keyword=keyword&vt_campaign=campaignid&vt_adgroup=adgroupid&vt_loc_interest=loc_interest_ms&vt_physical=loc_physical_ms&vt_matchtype=matchtype&vt_network=network&vt_placeme
AirManiax | Ads | Daily Budget Revision | Completed | Budget increased from AED180 to AED225
AirManiax | Ads | Revising attribution model | Completed | 30 days click to 3 week | 2025-07-21 | Airmaniax.com Contact ¦ Booking Form Interaction | Street Whatsapp Click SVD
AirManiax | Ads | Negative keyords revise | Completed | Search campaigns | 2025-07-21
AirManiax | Ads | Call number asset added to the asset | Completed | Search campaigns | 2025-07-21
AirManiax | Ads | WhatsApp extension added | On-hold
AirManiax | Ads | Structure snippets asset added | Completed | Search campaigns | 2025-07-21
AirManiax | Ads | Asset inventory refresh through new YouTube videos for PMax campaign. | Completed | Will upload New/Instagram videos on YouTube to use in ads. | 2025-07-31
AirManiax | Ads | 10% budget increased in the Pmax campaign | Completed | To improve conversions and ads score. | 2025-07-23
AirManiax | Ads | Bid strategy changed | Completed | Bid strategy changed from conversion value to maximise conversions | 2025-07-25
AirManiax | Ads | Awareness campaign on YouTube | On-hold | To increase the reach to customers | 2025-08-05 | New YouTube assets required
AirManiax | Ads | Shared website design inputs for CTA placement | Completed | Design team will pick up the changes
AirManiax | Ads | More negative keywords added to campaigns | Completed | Keywords related to mall contact no etc | 2025-07-25
AirManiax | Ads | Google tag implementation on roller.app payment page | In-Progress | To track conversion and refined remarketing/signals campaigns | 2025-08-06
AirManiax | Ads | New image/video assets for Pmax campaigns. | Completed | marked some new themes to build new content to reduce ads fatigue and more engagement. | 2025-07-31
AirManiax | Ads | First party data (email) upload on the Google ads account | In-Progress | Team will provide the data | 2025-07-31
AirManiax | Ads | Update the text ads with new copies | Completed | To refresh ads with improvised text copies | 2025-08-08
StreetManiax | Ads | New Google ad account created | Completed |  | 2025-08-02
StreetManiax | Ads | New Google tags created and shared for implementation | Completed | to track ads' performance | 2025-08-06
StreetManiax | Ads | Setting up Google Ads: https://ads.google.com/aw/billing/billingsetups?ocid=7474855848&ascid=7474855848&euid=1404235817&__u=4274393633&uscid=7469980266&__c=4486375834&authuser=2&__e=1556230347 | Awaiting input | Need payment details on the account. | 2025-08-02
AirManiax | Ads | DSA ads created in the search campaign | Completed | 2 new ads created with new copies for ad quality improvement testing | 2025-08-10
AirManiax | Ads | Campaign quality score for better optimisation | Completed | 90% score for Pmax and search campaign. | 2025-08-11
AirManiax | Ads | Actual sales mapping with campaigns performance. | On-hold | To assess the impact of campaigns with a change in the optimization strategy. Client does not have data of this to share with us. | 2025-08-17
AirManiax | Ads | Pmax Al Ain outlet Launch Campaign with offers from 15 Aug to 17 Aug | Completed | Launch Offers | 2025-08-15
AirManiax | Ads | Search Al Ain outlet Launch Campaign with offers from 15 Aug to 17 Aug | Completed | Launch Offers | 2025-08-15
AirManiax | Ads | Video View and Awareness Al Ain outlet Launch Campaign with offers from 15 Aug to 17 Aug | Completed | Launch Offers | 2025-08-15
AirManiax | Ads | Account level negative keywords | Completed | Added | 2025-08-20
AirManiax | Ads | Search campaign with keywords | In-Progress | Nad Al Sheba Dubai Outlet launch | 2025-08-29
AirManiax | Ads | Pmax with website click | In-Progress | Nad Al Sheba Dubai Outlet launch | 2025-08-29
AirManiax | Ads | Video View and Awareness | In-Progress | Nad Al Sheba Dubai Outlet launch | 2025-08-29
AirManiax | Ads | A/B test - New Ad group in Pmax - Broad Match | Completed | A/B performance testing | 2025-08-22
AirManiax | Ads | New Ad group in Pmax - (Audience-based) is 100% live | Completed | As per the result of the A/B test in Pmax campaign, the new ad group won in every KPI - CTR, Conversion and Cost/Conversion | 2025-08-22
AirManiax | Ads | Negative keywords removed from Campaigns | Completed | "Ferrari World near me", "cafe near me", "water world", "coffee shop near me", "warner bros worldtm yas island abu dhabi abu dhabi", "yas marina", "yas mall" | 2025-08-25
AirManiax | Ads | "Book Now: conversion action added in the campaigns. | Completed | To optimise campaigns to get more "Book Now" users (Online purchasers) to improve conversions. | 2025-08-22
AirManiax | Ads | Arabic Ad group in Pmax | In-Progress | Getting searches in Arabic in the Pmax campaign. Will make an A/B to check its performance. | 2025-08-29
AirManiax | Ads | Launch Remarketing campaign - dh1500/Month | In-Progress | On search and display network to target users who left the website without taking any action | 2025-08-29
AirManiax | Ads | Adding new business listings in Ads account | In-Progress | NAS and Al Jimi accounts | 2025-08-28